## Rate Definitions
Balconies Support and Remedial Works Framework
Section 5.3 Pricing Document - for notional scheme
MEASUREMENT PREAMBLES
The following are provided as indicative examples only and should be reviewed and adapted as necessary by the Client, prior to incorporation into any tender or other Contract documentation, to ensure that they are fully compatible with the maintenance service to be provided and the particular Schedule of Rates with which they are to be used.
Generally
Generally Rates Deemed to Include
A. | Rates for all Schedule of Rates items in all trades generally are deemed to include as appropriate for the following:
B | All work that can reasonably be deemed to be included either as good workmanship, including the provision of materials and plant, or accepted practice whether or not specifically referred to in this document, the Contract Administrator's decision on this will be final.
C | Clearing away all arisings, redundant materials, debris, rubbish etc., from site including damping down to reduce dust, loading into skips at ground level, skip hire or equivalent, transport and landfill and other waste disposal charges including any recycling costs.
D | The removal and disposal of all non regulated asbestos containing materials
E | Scaffolding, staging, towers, hoists, cradles and access ladders etc., as required including maintaining in accordance with appropriate safety regulations, clearing away on completion and making good all work damaged or disturbed.
F | Temporary supports, shoring or hoarding to existing structure including maintaining, adapting and clearing away on completion and making good all work damaged or disturbed.
G | Temporary dustproof, weatherproof and security screens, etc., as required and clearing away on completion and making good all work damaged or disturbed.
H | All setting and marking out, including provision and removal of temporary profiles.
I | Jointing and or finishing new materials including additional material where required.
J | Jointing and or finishing new materials to existing including additional material where required.
K | Matching all materials to existing.
L | Making good existing structure, finishings etc., as necessary.
M | Protecting the whole of the works.
Page 1

## Preliminaries
Balconies Support and Remedial Works Framework
Section 5.3 Pricing Document
Preliminaries - assume a 12 week on site period
|  |  | Set-up | Time Related | Removal | Total
Site Agent/ Working Foreman
QS;
Welfare
Storage
Plant and tools
Consumables
Insurances
Bond
Condition Survey
Post contract documents incl completion documentation
Scaffold licence
Scaffold design
Scaffolding
Site compound and hoarding; including design calculations
Temporay Lighting
Daily clean & Final Clean
Waste Management
Other -
|  | Totals carried to Pricing Summary £ | 0 | 0 | 0 | 0
Page 2

## Building Works
Balconies Support and Remedial Works Framework
Section 5.3 Pricing Document
Schedule of Rates for notional scheme
[Based on 2-74 Golden Grove - drg RP200058-S-3100 Type 1]
| Building Works |  |  | Rate | Total
|  |  |  | £ | £
1 | Site investigation | 1 | Item |  | 0
0
2 | Prepare site for piling works | 1 | Item |  | 0
0
3 | Hand dig to 750mm depth at pile locations | 12 | no. |  | 0
0
4 | Set up piling equipment on site | 1 | Item |  | 0
0
5 | Driven piling | Provisional |  | Sum | 10000
0
6 | Remove piling equipment from site | 1 | Item |  | 0
0
7 | Attendance on piling operation including removal of spoil | 1 | Item |  | 0
0
8 | Prepare heads of piles for incorporation in pile caps | 12 | no. |  | 0
0
9 | 900 x 300 x 300mm RC Pile caps including excavation, formwork and concrete | 12 | no. |  | 0
0
10 | 12mm Reinforcement in links in pile caps | 54 | kg |  | 0
0
11 | 16mm Reinforcement in pile caps | 71 | kg |  | 0
0
12 | 300 x 300mm Ground beam including excavation, formwork & concrete | 19 | m |  | 0
13 | 12mm Reinforcement in links in ground beams | 95 | kg |  | 0
0
14 | 20mm Reinforcement in ground beams | 140 | kg |  | 0
0
15 | Make good levels between new construction and adjacent existing surfacing | 1 | Item |  | 0
0
16 | Drill for and resin anchor in set of 4nr holding down bolts for steel columns | 12 | no. |  | 0
0
17 | 140 x 140 x 60kg SHS section steel column with spliced joints in storey height lengths | 3.2 | T |  | 0
0
18 | Fittings | 0.32 | T |  | 0
0
19 | 100 x 100 SHS tie beam | 2.24 | T |  | 0
0
20 | Fittings | 0.22 | T |  | 0
0
Page 3
21 | 100 x 100mm SHS beam in lengths not exceeding 3m | 1.15 | T |  | 0
0
22 | Fittings | 0.12 | T |  | 0
0
23 | 90 x 90 x 6mm RSA in 100mm lengths, welded to SHS and fixed to existing balconies with resin anchors [anchors measured separately] | 96 | no |  | 0
0
24 | 300 x 90mm PFC brackets in 1500mm lengths resin anchored to existing wall [anchors measured separately] | 12 | no |  | 0
0
25 | Resin anchors fixed to existing concrete soffits | 96 | no. |  | 0
0
26 | Ditto but to existing masonry | 48 | no |  | 0
0
27 | Paint steel framing | 154 | m2 |  | 0
0
28 | Touch up painting after erection of steel | 1 | Item |  | 0
0
29 | New 2800mm long Trespa infill panels at ground level including 50mm diameter framing and connections to main steel framing as drawing 3903 | 6 | no. |  | 0
0
30 | Set of four resin anchors into concrete beam for central pillar of infill panels | 6 | no. |  | 0
0
31 | Remove props and set aside for removal by others | 1 | Item |  | 0
32 | Clean/tidy site for handover | 1 | Item |  | 0
33 | Contractor to insert here any other foreseeable items he requires to be paid for:
0
|  | Carried to Pricing Summary £ |  |  | 10000
Page 4

## Additional rates
Balconies Support and Remedial Works Framework
Section 5.3 Pricing Document
Additional Rates for use as/when required
|  |  |  | Rate | £
1 | Extra over excavation rate for breaking out brickwork obstruction and removing from site | 5 | m3 |  | 0
2 | Ditto but concrete obstruction and removing from site | 5 | m3 |  | 0
3 | Ditto but reinforced concrete obstruction and removing from site | 5 | m3 |  | 0
4 | Extra over excavation rate for breaking out macadam or asphalt surfacing and removing from site | 10 | m2 |  | 0
5 | Extra over excavation rate for breaking out concrete surfacing less than 100mm thick and removing from site | 10 | m2 |  | 0
6 | Carefully expose live service encountered during pile cap excavations | 1 | Item |  | 0
7 | Alternative steel detail where glazing mullion would foul line of steel - see drg 3902; 2nr 150 x 150mm x 1250mm long RSA | 140 | kg |  | 0
8 | Rooftop detail on drawings 3200 & 3500; 75 x 150mm PFC in lengths not exceeding 3m resin anchored to existing wall [anchors measured separately] | 75 | kg |  | 0
9 | Rooftop detail on drawings 3200 & 3500; 70mm Diameter CHC section diagonal brace | 70 | kg |  | 0
10 | Fittings | 7 | kg |  | 0
11 | Rooftop detail on drawings 3200 & 3500; 305 x 102 UB section | 250 | kg |  | 0
12 | Fittings | 25 | kg |  | 0
13 | Spanning detail on drawing 3400; 533 x 210 x 102kg UB section | 1 | T |  | 0
14 | Fittings | 0.1 | T |  | 0
15 | Spanning detail on drawing 3400; web stiffeners | 0.06 | T |  | 0
16 | 180 x 180mm SHS columns as drawing 3400 | 2 | T |  | 0
17 | Fittings | 0.2 | T |  | 0
Page 5
18 | Drawing 3500; 150 x 100mm RSA | 33 | kg |  | 0
19 | Drawing 3600; 200 x 200mm SHS section columns | 1 | T |  | 0
20 | Fittings | 0.1 | T |  | 0
21 | Drawing 3600 spanning detail; 254 x 254 UC section beam | 0.65 | T |  | 0
22 | Fittings | 0.07 | T |  | 0
23 | Spanning detail on drawing 3600; web stiffeners | 0.05 | T |  | 0
24 | Drawing 3200; 100 x 100 SHS twice cranked tie as section Y-Y fixed with resin anchors to soffit of balcony/beam [resin anchors measured separately] | 6 | nr |  | 0
25 | Drawing 3902 detail on Type 4; Slab support detail comprising 100 x 100mm SHS 250mm long, welded structural Tee section welded into web of 533mm deep beam [beam measured separately] with 150 x 100mm RSA welded to other end of SHS and resin anchored to underside of concrete slab [resin anchors measured separately] | 3 | nr |  | 0
26 | Drawing 3400; New 500mm long Trespa infill panels at ground level including 50mm diameter framing and connections to main steel framing; see drawing 3903 | 1 | no |  | 0
27 | Drawing 3300; New 900mm long Trespa infill panels at ground level including 50mm diameter framing and connections to main steel framing; see drawing 3903 | 2 | no |  | 0
28 | Drawing 3400; Ditto but 1000mm long panel; see drawing 3903 | 1 | no |  | 0
29 | Drawing 3400; Ditto but 2000mm long panel; see drawing 3903 | 1 | no |  | 0
30 | Where disabled ground floor access is provided by means of ramps with key-klamp style barriers, level platforms outside of doors and at the foot of each ramp, access must be maintained to each dwelling. To ensure this, levels on ramp and lower platforms are to be raised to the upper platform level, barriers between dwellings removed and a new ramp created at the end of the block for access/egress. Price here for this provision for a single dwelling. | 4 | no |  | 0
31 | End ramp with key-klamp barriers | 2 | no |  | 0
32 | Provide temporary access to disabled ground floor dwelling when construction work prevents use of other routes. | 4 | no |  | 0
|  | Carried to Pricing Summary £ |  |  | 0
Page 6

## Framework offer summary
Balconies Support and Remedial Works Framework
Section 5.3 Pricing Document
Framework offer Summary
£
Preliminaries
| Set up cost |  |  |  | 0
| Time related cost |  |  |  | 0
| Removal cost |  |  |  | 0
| Building Works - Schedule of Rates |  |  |  | 10000
| Additional Rates |  |  |  | 0
| Preambles - from Section 4 |  |  |  | 0
Other items the Contractor wishes to insert:
|  |  |  | Total £ | 10000
| Contractor Overhead & Profit |  |  | % | 0
|  |  |  | Total £ | 10000
| Provisional Sum for Materials |  |  | 1000
| Overheads and profit on Materials % Add | Insert % | 15% | 150 | 1150
| Provisional Sum for Plant |  |  | 5000
| Overheads and profit on Plant, Access Equipement (eg. Cradles, Scaffolding, MEWP's etc.) Services, and Consumable Stores % Add | Insert % | 15% | 750 | 5750
| Provisional Sum for Sub Contractors |  |  | 1000
| Overheads and profit on Sub-Contractors % Add | Insert % | 10% | 100 | 1100
| Provisional Sum for Labour |  |  | 1000
| Overheads and profit on BCIS Daywork Rates % Add | Insert % | 10% | 100 | 1100
TOTAL CARRIED TO FORM OF TENDER £
19100
I / we confirm the prices stated above is a true and accurate reflection of the works described
Company……………………………………………………………
Address:………………………………………………………………………………
Tel No:…………………………………………………………………
Signed by:…………………………………………..…(Print name)
Capacity:………………………………………………………………
| Signature:……………………………………………………………… | Dated:………………………………

## Price
Lot 5.3 Scoring: Price
Tender Analysis
| Price 30% |  | Contractor:
|  |  | xxxx |  | xxxx |  | xxxx |  | xxxx
Preliminaries
Set up cost
Time related cost
Removal cost
Building Works - Schedule of Rates
Additional Rates
Preambles - from Section 4
Other items the Contractor wishes to insert:
|  | Total £ | 0 | Total £ | 0 | Total £ | 0 | Total £ | 0
| Contractor Overhead & Profit | % | 0 | % | 0 | % | 0 | % | 0
|  | Total £ | 0 | Total £ | 0 | Total £ | 0 | Total £ | 0
| Provisional Sum for Materials |  | 1000 |  | 1000 |  | 1000 |  | 1000
Overheads and profit on Materials % Add
|  | % | 0 | % | 0 | % | 0 | %
| Provisional Sum for Plant |  | 5000 |  | 5000 |  | 5000 |  | 5000
| Overheads and profit on Plant, Access Equipement (eg. Cradles, Scaffolding, MEWP's etc.) Services, and Consumable Stores % Add | % | 0 | % | 0 | % | 0 | %
| Provisional Sum for Sub Contractors |  | 1000 |  | 1000 |  | 1000 |  | 1000
| Overheads and profit on Sub-Contractors % Add | % | 0 | % | 0 | % | 0 | %
| Provisional Sum for Labour |  | 1000 |  | 1000 |  | 1000 |  | 1000
| Overheads and profit on BCIS Daywork Rates % Add | % | 0 | % | 0 | % | 0 | %
| Tender Value |  | 8000 |  | 8000 |  | 8000 |  | 8000
Post Tender Amendments:
| Amended Value |  | 8000 |  | 8000 |  | 8000 |  | 8000
Normalise x 30%

## Quality
Lot 3 Scoring: Quality
Quality Analysis |  | Quality 70%
|  |  | CLC |  |  |  | xxxx |  |  |  | xxxx |  |  |  | xxxx
| Question: | Criteria: | Score | Weighting | Total | Reason for Score | Score | Weighting | Total | Reason for Score | Score | Weighting | Total | Reason for Score | Score | Weighting | Total | Reason for Score
|  |  | 1 - 5 |  |  |  | 1 - 5 |  |  |  | 1 - 5 |  |  |  | 1 - 5
1 | Please provide an organisation structure identifying staff who will be involved with the day to day management of the work., with clear idenification of those involved with each sector of work, eg. Stage One (Surveys, Pre-fabrication Drawings) and Stage Two (Construction of Pad Foundations, Above Ground Supports to Balconies, and Balcony System).This should include operational and financial management/control. Additionally, please identify what resource will be made available to support the Contract from central sources. Please provide CVs for all key members of staff specifically those involved with the day to day running of the contract, giving details of their qualifications and training. |  | 4 | 3 | 12 | Generally good but project team have limited experience in this type of work |  | 3 | 0 |  |  | 3 | 0 |  |  | 3 | 0
2 | Please identify the location(s) of the office from which the day to day management of the contract will be undertaken. Please identify the location of any works depot that will be used to deliver the services if separate from the day to day management function location(s) and what office/welfare resources will be provided at each individual scheme. |  | 5 | 3 | 15 | Good local office, and good site set up |  | 3 | 0 |  |  | 3 | 0 |  |  | 3 | 0
3 | Please describe how the programme which you will compile in accordance with Preliminaries Clauses will be undertaken to ensure that the project will be completed within the contract duration as stated. Please provide a detailed critical path programme and methodology for the works indicating clear milestones and showing a clear understanding of the sequencing and challenges |  | 4 | 5 | 20 | Good programme covering all aspects |  | 5 | 0 |  |  | 5 | 0 |  |  | 5 | 0
4 | Please provide a detailed mobilisation programme indicating "lead in" periods for design approval and key pre-start operations |  | 5 | 5 | 25 | Well thought out and included S20 delays |  | 5 | 0 |  |  | 5 | 0 |  |  | 5 | 0
5 | Please provide details of your proposed site set-up on each site and how you will deal with parking restrictions, material deliveries and storage |  | 5 | 3 | 15 | well thought out site set up |  | 3 | 0 |  |  | 3 | 0 |  |  | 3 | 0
6 | Please describe the procedure you would follow for submitting fabrication drawings for approval, fabrication of steelwork, galvanising, powder coating, site delivery and erection and how you would ensure the protection of the finished steelwork during transportation and erection. Provide details of the organisations you would use for galvanising and powder coating, including location and if separate organisations the quality checking between galvanising and powder coating |  | 5 | 5 | 25 | Excellent description and identified issues |  | 5 | 0 |  |  | 5 | 0 |  |  | 5 | 0
7 | Please demonstrate how you propose to erect the steelwork frame whilst maintaining temporary support to the balconies |  | 3 | 4 | 12 | Quality plan incorrect but corrected at meeting and identified processes |  | 4 | 0 |  |  | 4 | 0 |  |  | 4 | 0
8 | Please provide information on how you will manage the Health and Safety requirements relevant to this contract and provide site supervisory details and relevant qualifications for all supervisory staff who might attend site to provide either Management or Health and Safety functions for this contact. As a minimum provide Name, Role, CSCS registration details. |  | 4 | 3 | 12 | Meets SCC requirements |  | 3 | 0 |  |  | 3 | 0 |  |  | 3 | 0
9 | Does your organisation have an up to date and regular reviewed policy on handling and exposure to asbestos and if so please provide a copy. Does your company provide asbestos awareness training and if so please provide details? Do you hold records showing that all appropriate staff have undergone recent and regular training and if so please provide details? |  | 4 | 4 | 16 | Meets SCC requirements |  | 4 | 0 |  |  | 4 | 0 |  |  | 4 | 0
10 | Please describe what measure you will adopt to ensure that a minimum of disruption is caused to the tenants of the properties in the individual schemes and surrounding neighbourhood whilst you are carrying out the works. Please describe the steps you will take to ensure resident access is not restricted at any time. What measures will you take to ensure that tenants are kept fully informed of the work to be undertaken at their address. |  | 4 | 4 | 16 | Good processes and includes the use of Whiteboards |  | 4 | 0 |  |  | 4 | 0 |  |  | 4 | 0
11 | Please provide details of any Enforcement or Prosecutions within the last 5 years in respect of Health & Safety failures, and if any please provide details of how your procedures have changed as a result of this |  | 4 | 4 | 16 | Enforcement notice and improvements. Not a critical event |  | 4 | 0 |  |  | 4 | 0 |  |  | 4 | 0
12 | Please confirm whether you are accredited to any Site Safety Schemes such as CHAS or Construction Line and if so provide evidence |  | 5 | 3 | 15 |  |  | 3 | 0 |  |  | 3 | 0 |  |  | 3 | 0
13 | Please explain how you will ensure good communication with the Employers management bodies and Employer and how you will ensure that information is passed on in a timely fashion so ensuring that all parties are aware in advance of the works that are being undertaken. What processes and procedures would you initiate to minimise disruption to neighbours and delays to the works. |  | 5 | 4 | 20 | Excellent communications plan |  | 4 | 0 |  |  | 4 | 0 |  |  | 4 | 0
14 | Please provide details of at least 2 similar projects that you have undertaken within the last 3 years of a similar nature and describe the works, how they relate to this project and the challenges you encountered and how these were resolved. Also include the value of the project and the overall contract period. |  | 4 | 5 | 20 | Both SCC and relevant to the project |  | 5 | 0 |  |  | 5 | 0 |  |  | 5 | 0
15 | Explain what risks may be encountered on this project and how they would be managed. |  | 3 | 2 | 6 | residents not identified as risks in plan but identified at interview |  | 2 | 0 |  |  | 2 | 0 |  |  | 2 | 0
16 | How will you ensure quality during the works? |  | 4 | 3 | 12 | Meets SCC requirements |  | 3 | 0 |  |  | 3 | 0 |  |  | 3 | 0
17 | Are your environmental management processes and procedures certified to a recognised standard (eg ISO14001, EMAS) by a third party certification body and if so please provide details? Are your quality management processes and procedures certified to a recognised standard by a third party certification body and if so provide details? |  | 5 | 3 | 15 |  |  | 3 | 0 |  |  | 3 | 0 |  |  | 3 | 0
18 | Please indicate all the works that you will sub-contract including major subcontractors/suppliers and provide the names and addresses of any key sub-contractors/suppliers you will employ. Giving the percentage of the overall spend you intend to deliver using the sub-contractor. |  | 4 | 3 | 12 | 85% sub-contract |  | 3 | 0 |  |  | 3 | 0 |  |  | 3 | 0
19 | Please describe what measure you or your sub-contractors will take with regards to the employment of local residents including the employment of NEETS and what if any apprenticeship scheme you will operate within Southampton as part of this refurbishment programme. |  | 4 | 3 | 12 | Meets SCC requirements |  | 3 | 0 |  |  | 3 | 0 |  |  | 3 | 0
20 | Explain how you as a company are working towards the goal of "nil defects" and what provision will be made for rectifying latent defects. |  | 4 | 3 | 12 | Good processes |  | 3 | 0 |  |  | 3 | 0 |  |  | 3 | 0
21 | Please confirm the piling method that you have included within your tender and the reasons for selecting this piling method |  | 5 | 3 | 15 | Meets SCC requirements and deals with the reason for the choice of pile |  | 3 | 0 |  |  | 3 | 0 |  |  | 3 | 0
22 | Please provide details of the methodology that you propose to use for the erection of the steelwork and the proposed plant and how you intend to maintain resident access to and from their flats during the course of the works |  | 3 | 5 | 15 | Reasonable response but does not cover matters like "school runs" etc |  | 5 | 0 |  |  | 5 | 0 |  |  | 5 | 0
| Total Score |  |  |  | 338 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| Normalise to percentage of 400pts |  |  |  | 84.5% |  |  |  | 0% |  |  |  | 0% |  |  |  | 0%

## Combined
Lot 3 Scoring: Combined
Combined Tender Score
|  |  | Total Points | Adjustment | Adjusted Points | Total | Ranking
| CLC | Price (30%) |  |  | 30
|  | Quality (70%) | 84.5% | 0.7 | 59.15
|  | Total |  |  |  | 89.15
| xxxx | Price (30%) |  |  | 0
|  | Quality (70%) | 0% | 0.7 | 0
|  | Total |  |  |  | 0
| xxxx | Price (30%) |  |  | 0
|  | Quality (70%) | 0% | 0.7 | 0
|  | Total |  |  |  | 0
| xxxx | Price (30%) |  |  | 0
|  | Quality (70%) | 0% | 0.7
|  | Total |  |  |  | 0