# Action Plan Template

Strawberry Fields fun day

Sunday 19th September 2010

| DATE | ACTION | PERSON | ACHIEVED |
| --- | --- | --- | --- |
| 15 April | Confirmed dates and times: Sunday 19th Sept, time 12.30 – 3.30 |  |  |
|  | Arrange Public Liability Insurance | Pete |  |
|  | Funding applied for | Susan |  |
|  | Make list of possible ideas for day | All |  |
|  | Contact people and groups on ideas list | All |  |
|  | First Aid cover | Mike and Carol |  |
| 20 May | Decide who could open the event and invite | Jackie |  |
|  | Make Budget | Carol |  |
|  | Temporary events licence: apply for | Pete |  |
|  | Grass cutting of park – Need to book | Mike |  |
|  | Book / arrange to borrow gazebos | Carol |  |
|  | Book PA system: | Carol |  |
|  | Draft design for publicity (use basis of last year’s?) | Jack |  |
|  | Publicity channels – Local papers, radio stations etc | Jack |  |
| 17 June | Events timetable drafted | Bev |  |
|  | Publicity agreed, produce posters etc | Mike |  |
|  | Layout plan of area | Bev |  |
|  | Find extra volunteers for the day | All |  |
|  | Any help required from SCC |  |  |
|  | Agree who will do what on the day | Bev |  |
| 15 July | Publicity drive / flyers distributed | All |  |
| 19 August | Prepare the area, arrange for rubbish bins | Mike |  |
|  | Risk assessments completed | Carol |  |
|  | Confirm attendance all key people | All |  |
|  | Clearing up arrangements | All |  |
|  | Who will help with Gazebo’s Marquees | All |  |
|  | Public Opinion evaluation of the day (opinion meter?) | All |  |
| 19 Sept | GALA DAY takes place!!!!! |  |  |
| 30 Sept | Evaluation “Wash up” meeting |  |  |
|  | Thank you’s etc |  |  |
|  | Check budget |  |  |
|  | Complete any funding returns |  |  |